## Road Map
WePOS
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 10/28/2025 | SPRINT2 - 11/18/2025 | SPRINT3 - 12/16/2025
01. User Access & Security | 01.01 Sign Up | 4 | x
| 01.02 Log In | 3 | x
| 01.03 Log Out | 4 | x
| 01.04 Reset Password | 4 | x
| 01.05 Update Profile | 3 |  | x
| 01.06 Delete Account | 2 |  | x
| 01.07 Email Notifications | 2
02. Menu & Inventory Control | 02.01 Create Menu Item | 4 | x
| 02.02 Update Menu Item | 4 |  | x
| 02.03 Delete Menu Item | 4 | x
| 02.04 Schedule Availability | 4 |  | x
| 02.05 Sync Availability Updates | 4 |  |  | x
| 02.06 Adjust Pricing | 2
03. Order Lifecycle Management | 03.01 Receive Online Order | 4 |  | x
| 03.02 Cancel Order | 4 |  | x
04. Delivery Platform Integration | 04.01 Integrate via REST/WebSockets | 5 |  | x
| 04.02 Ingest Orders from Partners | 4 |  |  | x
| 04.03 Simulate Integration (Mock APIs) | 4
| 04.04 Log Integration Errors | 3
| 04.05 Secure Data Exchange (TLS/HTTPS) | 4 |  |  | x
| 04.06 Sync Menu with Partners | 2 |  |  | x
05. Business Insights & Reporting | 05.01 Generate Sales Report | 4 |  |  | x
| 05.02 Export Data | 3 |  |  | x
| 05.03 Monitor Delivery Performance | 3
| 05.04 Channel Volume Dashboard | 4
|  | VELOCITY: | 23 | 26 | 24

## Jira Road Map
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board