## Sheet1
Sprint 1: Daily Schedule, Week 8 |  |  |  | Planned |  | Distributed
Tasks | Owner | Tuesday -Day 1 | Wednesday -Day 2 | Thursday -Day 3 | Friday -Day 4 | Saturday -Day 5 | Sunday -Day 6 | Monday -Day 7(leftovers)
Create and distribute a Daily Schedule for the week, include Stories to implement this week | Anirudh | X | X | X | X | X | X
S2: RCT - Planning (with Crosscuts) | Jyot | X | X | X | X
S2: Supplementary Requirements (S2 crosscut details) | Gowthami,Kalyani | X | X | X | X
S2: Burndown Chart (Excel) | Gowthami | [5 empty] | X | X
S2: Kanban Board in Jira | Dinesh |  |  | X | X | X | X
S2: List of Story Tasks (use ChatGPT to identify tasks) | Nikitha | X | X | X | X
S2: Include a few critical tasks in Jira for tracking in Kanban Board | Dinesh | X | X | X | X
S2: Dataflow Diagrams (2) (logical, S2 scope) | Swathi,Sindu | X | X | X | X
S2: Start implementing User Stories according to the RoadMap | Lavanya | X | X | X | X | X | X
S2: Jenkins Progress Report (S2 planning) | Chetan |  |  |  |  | X | X
01.05 Update Profile |  | X | X | X | X | X | X
01.06 Delete Account |  | X | X | X | X | X | X