## User Stories
USER STORIES - WEPOS
Module | Title | As a/an | I want to... | So that I can... | Sprint | Story Points | Story Constraints | Story Exceptions
01. User Access & Security | 01.01 signup | Restaurant Admin,AccountManager | create an account | access the WEPOS platform and manage my store | S1 | 4 | Email must be unique and password must meet security standards | If email is already registered or password is weak, signup will fail
| 01.02 Log In | Account Manager,Accountant,Daily need manager,Integration Engineer,Restaurant Operation Team,Restaurant Admin | log into my account | access my dashboard and perform tasks | S1 | 3 | Credentials must match stored records | If credentials are incorrect or server is down, login will fail
| 01.03 log out | Account Manager,Accountant,Daily need manager,Integration Engineer,Restaurant Operation Team,Restaurant Admin | log out of my account | ensure my session is securely closed | S1 | 4 | Session must be active to log out | If session has expired or connectivity is lost, logout may not complete
| 01. 04 Reset Password | Account Manager,Restaurant Admin,Daily Need Manager,Restaurant Operation Team, | reset my password | regain access if I forget my credentials | S1 | 4 | Email must be verified before password reset | If email is invalid or reset link expires, password cannot be reset
| 01.05 Update Profile | Restaurant Admin,Accountant,Daily need manager,Restaurant Operation Team,Restaurant Admin | update my profile details | keep my information accurate and current | S2 | 3 | Only authenticated users can update profile | If required fields are missing or invalid, update will fail
| 01. 06 Delete Account | Account manager, Restaurant Admin | delete my account | permanently remove my data from the system | S2 | 2 | Only verified users can delete their account | If user is not authenticated or deletion conflicts with active orders, request will be denied
| 01.07 Email Notification | Account manager, Restaurant Admin | receive email notifications | stay informed about orders and updates | TBD | 2 | User must opt-in for notifications | If user has opted out or email service is down, notifications will not be sent
02. Menu & Inventory Control | 02.01 Create Menu Item | Daily need manager/Recipe Specialist,Restaurant Admin | add new items to the menu | offer updated products to customers | S1 | 4 | Item name, price, and category must be provided | If required fields are missing or duplicate item exists, creation will fail
| 02.02 Update Menu Item | Daily need manager/Recipe Specialist,Restaurant Admin | edit existing menu items | reflect changes in product details | S2 | 4 | Only authorized users can update menu items | If item ID is invalid or server is down, update will fail
| 02.03 Delete Menu Item | Daily need manager/Recipe Specialist,Restaurant Admin | remove items from the menu | keep the menu clean and relevant | S1 | 4 | Only inactive items can be deleted | If item is linked to active orders or inventory, deletion will be blocked
| 02.04 Schedule Availability | Daily need manager/Recipe Specialist,Restaurant Operation Team,Restaurant Admin | set item availability by time | control when items are offered | S2 | 4 | Time slots must be valid and not overlap | If schedule conflicts or time format is invalid, availability will not be saved
| 02. 05 Sync Availability Updates | Daily need manager/Recipe Specialist,Restaurant Operation Team,Integration Engineer,Restaurant Admin | sync item availability across platforms | ensure consistency across delivery partners | S3 | 4 | Sync requires active API connection with delivery platforms | If API fails or platform is offline, sync will not complete
| 02. 06 Adjust Pricing | Daily need manager/Recipe Specialist,Restaurant Admin | change item prices | reflect promotions or cost changes | TBD | 2 | Price must be within allowed range and formatted correctly | If price is invalid or update conflicts with active discounts, change will fail
03. Order Lifecycle Management | 03.01 Receive Online Order | Restaurant Operations Team,Restaurant Admin | receive orders from customers | fulfill them efficiently | S2 | 4 | Orders must include valid items, quantities, and payment confirmation | If order is incomplete, payment fails, or system is down, order will not be received
| 03.02 Cancel Order | Restaurant Operations Team,Restaurant Admin | cancel an order | handle customer changes or errors | S2 | 4 | Only orders not yet prepared or dispatched can be canceled | If order is already in delivery or completed, cancellation will be denied
04. Delivery Platform Integration | 04.01 Integrate via REST/WebSockets | Integration Engineer,Restaurant Admin | connect WEPOS with delivery platforms | enable real-time order sync | S2 | 5 | API keys and endpoint URLs must be valid | If credentials are invalid or endpoint is unreachable, integration will fail
| 04.02 Ingest Orders from Partners | Integration Engineer,Restaurant Admin | receive orders from external platforms | manage all orders in one place | S3 | 4 | Partner systems must be online and authenticated | If partner API is down or data format is invalid, orders will not be ingested
| 04.03 Simulate Integration(Mock APIs) | Integration Engineer,Restaurant Admin | test integrations before going live | ensure stability and accuracy | TBD | 4 | Mock endpoints must be configured and return expected responses | If mock server is misconfigured or returns errors, simulation will fail
| 04.04 Log Integration Errors | Account Manager,Integration Engineer,Restaurant Admin | track integration issues | troubleshoot problems quickly | TBD | 3 | Logs must capture timestamp, error code, and source platform | If logging service is down or data is incomplete, errors may not be recorded
| 04.05 Secure Data Exchange (TLS/HTTPS) | Integration Engineer,Restaurant Admin | encrypt data transfers | protect sensitive customer and order data | S3 | 4 | All endpoints must support HTTPS and TLS 1.2+ | If insecure protocols are used or certificates are invalid, data exchange will be blocked
| 04.06 Sync Menu with Partners | Integration Engineer,Restaurant Admin | push updated menu to delivery platforms | ensure customers see correct items | S3 | 2 | Sync requires valid credentials and active connection | If sync fails due to API errors or outdated tokens, menu will not update
05. Business Insights & Reporting | 05.01 Generate Sales Report | Account Manager,Accountant,Daily need manager,Restaurant Admin | view sales performance | analyze revenue and trends | S3 | 4 | Report must include date range, item breakdown, and totals | If data is missing or filters are invalid, report will not generate
| 05.02 Export Data | Account Manager,Accountant,Restaurant Admin | export reports to CSV or Excel | share insights with stakeholders | S3 | 3 | Export format must be selected and data must be complete | If export fails due to format errors or server timeout, file will not be created
| 05.03 Monitor Delivery Performance | Account Manager,Integration Engineer,Restaurant Admin | track delivery metrics | improve service quality | TBD | 3 | Metrics must include delivery time, ratings, and order status | If delivery data is incomplete or delayed, performance metrics will be inaccurate
| 05. 04 Channel Volume Dashboard | Account Manager,Accountant,Daily need manager,Restaurant Operation Team,Restaurant Admin | view order volume by channel | optimize marketing and operations | TBD | 4 | Dashboard must pull data from all integrated platforms | If any platform fails to sync or data is outdated, dashboard will show incomplete results